## Foglio1
[11 empty] | TOTAL PROJECT DAYS |  | 19 days
START DAY:
[7 empty] | 2018-12-04 |  |  |  |  | Critical Path
Gui Requirement
Start Day: | 2018-12-04 | Task ID: | 1
Finish Day: | 2018-12-07 | Duration: | 3 days
Architecture v2
[10 empty] | Start Day: | 2018-12-04 | Task ID: | 4
|  |  | Business Logic Requirement | [6 empty] | Finish Day: | 2018-12-05 | Duration: | 1 day
|  |  | Start Day: | 2018-12-07 | Task ID: | 2
|  |  | Finish Day: | 2018-12-10 | Duration: | 3 days
ER Design
[13 empty] | Start Day: | 2018-12-05 | Task ID: | 8
[6 empty] | DB Requirement | [6 empty] | Finish Day: | 2018-12-06 | Duration: | 1 day
[6 empty] | Start Day: | 2018-12-10 | Task ID: | 3
[6 empty] | Finish Day: | 2018-12-13 | Duration: | 3 days | Class Diagram
[10 empty] | Start Day: | 2018-12-05 | Task ID: | 7
[10 empty] | Finish Day: | 2018-12-08 | Duration: | 3 days
| FR Revision |  |  |  |  | Prioritization Revision
| Start Day: | 2018-12-13 | Task ID: | 5 |  | Start Day: | 2018-12-10 | Task ID: | 6
| Finish Day: | 2018-12-14 | Duration: | 1 day |  | Finish Day: | 2018-12-13 | Duration: | 3 days
| NFR Revision |  |  |  |  | Design Decision Revision
| Start Day: | 2018-12-14 | Task ID: | 9 |  | Start Day: | 2018-12-13 | Task ID: | 10 |  | Prototipo v1/Database/Interfaccia v.1
| Finish Day: | 2018-12-15 | Duration: | 1 day |  | Finish Day: | 2018-12-16 | Duration: | 3 days |  | Start Day: | 2018-12-08 | Task ID: | 13
[11 empty] | Finish Day: | 2018-12-22 | Duration: | 14 days
| How FR & NFR are satisfied |  |  |  |  | Assumption/Exluded R. Revision
| Start Day: | 2018-12-16 | Task ID: | 11 |  | Start Day: | 2018-12-16 | Task ID: | 12
| Finish Day: | 2018-12-21 | Duration: | 5 days |  | Finish Day: | 2018-12-19 | Duration: | 3 days
Deliverable Revision
[6 empty] | Start Day: | 2018-12-22 | Task ID: | 14
[6 empty] | Finish Day: | 2018-12-23 | Duration: | 1 day