## Foglio1
Functional Requirement
| Start Day: | 2018-11-16 | Task ID: | 1
| Finish Day: | 2018-11-23 | Duration: | 7 days | Prioritization |  |  |  | Design Decision
[5 empty] | Start Day: | 2018-11-23 | Task ID: | 4 | Start Day: | 2018-11-26 | Task ID: | 6
| Exluded Requirement |  |  |  | Finish Day: | 2018-11-25 | Duration: | 3 days | Finish Day: | 2018-11-30 | Duration: | 5 days |  |  |  |  | Deliverable Revision
START DAY: | Start Day: | 2018-11-16 | Task ID: | 2 | [12 empty] | Start Day: | 2018-12-01 | Task ID: | 9
2018-11-16 | Finish Day: | 2018-11-23 | Duration: | 7 days | Assumption |  |  |  | Component diagram |  |  |  | Sequence diagram |  |  |  | Finish Day: | 2018-12-02 | Duration: | 1 day
[5 empty] | Start Day: | 2018-11-23 | Task ID: | 5 | Start Day: | 2018-11-27 | Task ID: | 7 | Start Day: | 2018-11-30 | Task ID: | 8
| Non Functional Requirement |  |  |  | Finish Day: | 2018-11-26 | Duration: | 4 days | Finish Day: | 2018-11-30 | Duration: | 4 days | Finish Day: | 2018-12-01 | Duration: | 2 days
| Start Day: | 2018-11-16 | Task ID: | 3
| Finish Day: | 2018-11-23 | Duration: | 7 days
Critical Path
TOTAL PROJECT DAYS | 18 days