## Foglio1
[11 empty] | TOTAL PROJECT DAYS |  | 24 days
START DAY:
[6 empty] | 2018-12-27 | [5 empty] | Critical Path
Scenarios Revision
[8 empty] | Start Day: | 2018-12-27 | Task ID: | 2
Gui Revision | [7 empty] | Finish Day: | 2018-12-29 | Duration: | 2 days
Start Day: | 2019-01-10 | Task ID: | 4
Finish Day: | 2019-01-20 | Duration: | 10 days | [10 empty] | Schema ER Revision
[14 empty] | Start Day: | 2019-01-05 | Task ID: | 8
|  |  |  | Completamento Prototipo |  |  |  |  | Architecture v3 |  |  |  |  | Finish Day: | 2019-01-06 | Duration: | 1 day
|  |  |  | Start Day: | 2018-12-27 | Task ID: | 1 |  | Start Day: | 2018-12-29 | Task ID: | 3
|  |  |  | Finish Day: | 2018-01-19 | Duration: | 23 days |  | Finish Day: | 2019-01-05 | Duration: | 7 days
Sequence Diagram Revision
[9 empty] | Class Diagram Revision |  |  |  |  | Start Day: | 2019-01-08 | Task ID: | 8
[9 empty] | Start Day: | 2019-01-05 | Task ID: | 3 |  | Finish Day: | 2019-01-08 | Duration: | 1 day
[9 empty] | Finish Day: | 2019-01-07 | Duration: | 2 days
FR e NFR Revision
[10 empty] | Start Day: | 2019-01-07 | Task ID: | 3
[10 empty] | Finish Day: | 2019-01-10 | Duration: | 3 days
Deliverable Revision
[6 empty] | Start Day: | 2019-01-10 | Task ID: | 4
[6 empty] | Finish Day: | 2019-01-20 | Duration: | 10 days